## Stakeholder
All video meetings on Google Meet, all documenations and information using Jira & Confluence
ID | Stakeholder's Name | Project Role (if any) | Key Interests and Issues | Communication Approach (from Power/Interest Grid)1 | Current Status2 | Desired Support3 | Contact details | Action and Communication
1 | Alisher Dosodov | Project Manager | Project timelines, budget management, team coordination | Manage Closely | Advocate | High | Telegram - @random | Conducts daily stand-up meetings to review progress and address issues. Sends weekly progress reports to stakeholders summarizing project status.
2 | Zaman Kayirov | Product Owner | Product vision, user needs, feature prioritization | Manage Closely | Critic | High | product.owner@gmail.com | Holds weekly meetings with the development team to prioritize features and gather feedback. Communicates regularly with stakeholders to gather requirements.
3 | Amir Yerzhanov | Technical Director | Technology stack, system architecture, scalability | Monitor | Advocate | Medium | 775547646464 | Provides bi-weekly technology updates to the team, addressing any technical challenges. Coordinates with developers to ensure system stability and performance.
4 | Damir Kassenov | Team Lead - Backend | Team performance and resource allocation | Manage Closely | Supporter | High | 777756787956 | Conducts bi-weekly code reviews and coordinates integration efforts with other team leads.
5 | Kenessary Hamdula | Team Lead - Frontend | User interface design, user experience, frontend tech | Manage Closely | Supporter | High | 770123476544 | Leads weekly design reviews to iterate on interface designs. Collaborates with backend developers to ensure seamless integration.
6 | Ismail Kasymzhanov | Team Lead - Mobile | Mobile app development, Android platform, user engagement | Manage Closely | Supporter | High | 77753450978 | Holds daily sync meetings with mobile developers to discuss progress and align with user needs.
7 | Yerkebulan Agelbek | Team Lead - QA | Testing processes, test automation, product quality | Keep informed | Supporter | High | 77759253478 | Conducts weekly test plan reviews and provides updates on testing progress. Ensures bug triage and resolution with the team.
8 | Daniyar Bakhytov | System Analyst | System requirements, process modeling, documentation | Manage Closely | Supporter | High | Telegram - @fagtek | Communicates with business analysts and developers to clarify system requirements and document specifications.
9 | Beisembay Bolatov | Business Analyst | Business requirements, business process modeling | Manage Closely | Supporter | High | Telegram - @greterd | Gathers business requirements and collaborates with system analysts to translate them into technical specifications.
10 | Asiya Bazhanovna | Designer | User interface design, branding | Manage Closely | Supporter | High | 77775672345 | Conducts weekly design mockup reviews and collaborates with developers to ensure design feasibility.
11 | Dimash Zhabanov | Backend Developer | Backend coding, database management | Keep informed | Supporter | High | Telegram - @greatlead | Daily meeting; Provides daily code updates and collaborates with frontend developers for integration.
12 | Zhanerke Aitulova | Frontend Developer | Frontend coding, user interface implementation | Keep informed | Supporter | High | Telegram - @reistern | Daily meeting; Aligns daily with UI/UX designers to implement designs. Collaborates with backend developers for consistent functionality.
13 | Abzal Gabibov | Mobile Developer | Mobile app development, user interface, platform-specific features | Keep informed | Supporter | High | 77771002350 | Daily meeting; Communicates daily with the product owner to align development efforts. Integrates features with backend services.
14 | Sanzhar Menbekov | QA Tester | Test case execution, bug reporting, test automation | Keep informed | Supporter | High | 77019899898 | Daily meeting; Executes test cases daily and provides regular feedback on bug fixes.
15 | Bakhytzhan Zardaulet | Sponsor | Project success, ROI, strategic alignment | Keep satisfied | Neutral | Low | 77015893049 | Receives monthly project updates and provides strategic guidance. Advocates for project success.
16 | Alma Delzhanovna | Fashion Influencer | Trend analysis, fashion advice, user engagement | Keep Satisfied | Neutral | Low | fashion.consultant@gmail.com | Participates in bi-weekly brainstorming sessions and shares feedback on app features and trends.
17 | Gleb Frolov | Local Store Representative | Insights on local fashion preferences, market trends, promotional events. Integration support for the mobile app | Manage Closely | Supporter | Medium | fsfsf@gmail.com | Attends monthly meetings to provide insights on local fashion preferences and market trends. Collaborates on local promotional events.
18 | Andrew Smtith | Foreigner Store Representative | Insights on global market trends, alignment with foreigners stores. Integration support for the mobile app | Manage Closely | Supporter | Medium | balbander@gmail.com | Provides monthly market reports and collaborates on global market alignment.
19 | Gabe Fredler | Marketing Manager | User acquisition, brand awareness, marketing campaigns | Manage Closely | Supporter | High | marketing@company.com | Develops and executes marketing strategies. Coordinates with the team to align marketing efforts with project goals. Conducts market research and analysis to identify opportunities and trends.

## RACI
Activities | Project Manager | Product Owner | Technical Director | Team Lead - Backend | Team Lead - Frontend | Team Lead - Mobile | Team Lead - QA | System Analyst | Business Analyst | Designer | Backend Developer | Frontend Developer | Mobile Developer | QA Tester | Sponsor | Local Store Representative | Foreigner Store Representative | Marketing Manager
Project Timelines | R | C | I | I | I | I | I
Budget Management | R | I | I | I | I | I | I
Team Coordination | A/R | I | I | I | I | I | I
Product Vision | I | R | A | I | I | I | I
Manage Risk | A | C | I | I | I | I | I | I | R
Feature Prioritization | I | R | A | I | I | I | I
Development | I | I | C | A | A | I | I |  |  |  | R | R | R
System Architecture | bar: A to I
User Interface Design | I | C | I | I | R | I | I |  |  | R
Mobile App Development | I | C | I | I | I | A | I | [5 empty] | R
Testing Processes | [13 empty] | R | bar: A to I
Quality Assurance | [13 empty] | R | bar: A to I
Business Requirements | I | C | I | I | I | I | I |  | R
Process Modeling | I | C | I | I | I | I | I | R
Business Documentation | I | C | I | I | I | I | I |  | A/R
System Documentation | I | C |  | I | I | I | I | A/R
Marketing Strategy | [15 empty] | C | C | A/R | bar: A to I
UAT | [16 empty] | R | R | bar: A to I
Demo | A | I | I | C | C | C | C |  | R